云 南 省 绿 卡 INTRANET 网 络

工 程 实 施 报 告

目  录

第 一 章 、 工 程 管 理	4

1、工 程 管 理 的 工 作 目 标	4

2、工 程 管 理 内 容	5

A、详 细 工 程 计 划	5

B、基 于 工 程 计 划 协 调 工 程 进 展	5

C、工 程 管 理	6

D、人 力 资 源 和 设 备资 源 的 统 一 管 理	6

E、统 一 协 调	6

3、工 程 管 理 计 划 (PMP)	6

4、工 程 协 调 会	7

5、文 档 管 理	7

第 二 章 、工 程 实 施	8

实 施步 骤  ：

1：工 程 准 备 阶 段	8

2：硬 件 安 装 联 调 阶 段	8

3：工 程 初 验	9

4：试 运 行 及 终 验	9

具 体 实 施 ：

1．项 目 进 度 表：	10

2．准 备 工 作 要 求	10

3．网 络 拓 扑 结 构	11

4、网 络 设 备 命 名 规 则	13

5．线 路 情 况 说 明	13

6．地 址 分 配	13

7．路 由 规 划	15

8．云南绿卡网络的具体技术特性，可靠性、冗余备份	17

第 三 章、 技 术 支 持 与 服 务	19

1、技 术 支 持 力 量	19

2、售 后 服 务	19

3、保 修 服 务	20

4、技 术 支 持 服 务 时 间 及 人 员	20

第 四 章 、网 络 设 备 安 装	21

1、云 南 绿 卡  过 程 工 程 中 心 点 安 装 实 施	21

2、电 路 情 况调 查 表	22

3、 机 房 情 况 调 查 表	22

4、 大 理 、 玉 溪  中 心 LAN 的 调 整	23

5、 地 州、县 局 的 安 装	23

第 五 章 、工 程 实 施 验 收	25

1、 数 据 网 络 的 连 通 性 测 试	25

2、 IP电 话 的 连 通 性 及 效 果 测 试  	25

3、 备 份 线 路 、 备 份 路 由 的 测试	26

4、 网 络 路 由 汇 聚 的 测 试	26

5、 网 管 系 统 的 功 能 测 试	26

第六章、工 程 文档	27

1、 安 装 报 告   	27

2、 验 收 报 告   	32

3、 IP 地 址 分 配 表   	35

4、 IP 电 话 号 码  表   	37

5、 设 备 技 术 参 数    	37

6、 设 备 配 置 参 数    	37

# 第 一 章 、工 程 管理

## 1、工 程 管 理 的 工作 目 标

XX 科 技 有 限 公 司 充 分 认 识 到 一 个 数 据、语 音 网 络 工 程 实 施 成 功 的 标 志 是： 按 时、 有 序、 保 质 地 完 成 一 个 统 一 的 数 据 、 语 音 通 信 系 统 ， 而有 效 的 工 程 督 导 是 整 个 工 程 实 施 取 得 成 功 的 关 键。 XX 公 司 自 一 九 九 一 年 进 入 中 国 市 场 以 来， 先后 在 金 融、 油 田、 电 信、 邮 政、 政 府 等 多 个 领 域 展 开 合 作， 是 目 前 在 中 国 具 备 实 施 基 于 CISCO 设 备的  全 国  数 据 、 语 音 通 信 网 工 程 实 际 经 验 的 专 业 性 网 络 集 成 公 司。 基 于 多 年 的 工程 经  验， XX 公 司 具备 一 套 行 之 有 效 的 工 程管 理 程 序， 可 以 保 证用 户 数 据 网 络 项 目 的 顺 利 完 成。

XX 公 司 将 向 用 户 提 供 有 效 的 工 程 实 施 质量 控 制 程 序 ， 确 保 云 南 绿 卡 网 络 工 程 的 质 量 和 进 度 。 该 程 序 包 括 设 计 细 化 认 证、 人 力 资 源 管 理（项 目 领 导 小 组 确 认）、 产 品 和 材 料 管 理、 工 程 和 技 术 档 案 管 理 等。 所 有 相 关 的技 术 资 料 和 操 作 手 册将 及 时 提 供 给 用 户 有 关 机 构 的 管 理 人 员， 以 便 用 户 及 时 掌 握 和 了 解 这 些 技 术。

## 2、工 程 管 理 内 容

XX 公 司 将 向 用 户 提 供 一 个 行 之 有 效 的 工 程 管 理 方 案 和 详 细 的 工程 实 施 计 划。 在 该 程 序 之 中， 最 重 要 的 是 项 目 进 程 的 管 理。

XX 公 司 将 为 数 据 网 络 工 程 组 建 一 个 工 程 实 施  小 组， 其 中 包 括 项 目 经 理、 高 级 工 程 咨 询 人 员 CCIE、 以 及 技 术 工 程 师。 同时， 为 能 够 在 工 程 实 施 过 程 中， 各 项 工 作 能 够 得 到 用 户 方 面 的 配 合， XX 公 司 建 议 成 立 一 个 项 目领 导 小 组， 领 导 小 组 成 员 由 用 户 代 表（至 少 一 人）和 XX 公 司 负 责 本 项 目 的 客 户 经 理 组  成， 当 工 程 实 施 过 程 中， 如 遇 到 工 程 实 施 小 组 项目 经 理 不 能 单 方 面 确 认 的 问 题 时， 则 向 项 目 领 导 小 组 反 馈 并 得 到 确 认。

XX 公 司 的 技 术 工 程 师 会 完 成 所 有 与 设 备 现 场 安 装 有 关的 技 术 工 作，诸 如： 技 术 资 料 准 备 、 网 络 测 试、 现 场 安 装 和 验 收 测 试。 为 了 实 现 工 程 管 理 的 目 标， 具 有 良 好 的技 术 背 景 和 工 程 经 验 的 工 程 专 家 将 被 任 命 为 项 目 经 理， 项 目 经 理 将 负 责 计 划 和 督 导 整 个 工 程 的实 施。 项 目 经 理 将 全 面 负 责 理 解 和 协 调 在 工 程 实 施 中 各 方 面 的 工作 。  工 程 管 理 包 括 以 下 具 体 内 容：

### A 、详 细 工 程 计 划

根 据 实 际 安 装 条 件 、 设 备 生 产 期 限、 人 力 资 源 状 况、 传 输 系 统 状 况 和 其 它各 种 现 实 因 素， 项 目 经 理 全 面 规 划一 个 符 合 实 际 的 整 个 工 程 进 度 计 划， 其 中 包 括： 各 阶 段 的 具 体工 作 内 容、 以 及 各 阶 段 完 成 工 作 的 定 义。 在 得 到 用 户 有 关 方 面 的 同 意 之 后， 项 目 经 理 将 对 整 个 工程 进 展 进 行 协 调， 并 在 保 证 工 期 、 质 量、 和 减 少 成 本 的 前 提 下 对 工 程 各 个 阶 段 采 取 必 要 的 督 导和 控 制 。

在 工 程 开 工 协 调 会 后 ， XX 公 司 项 目 经 理 将 向 用 户 方 提 供 详 细 工 程 计 划表， 对 工  程 实 施 的 各 个 环 节 作 出 工 程 进 度安 排 。

### B 、基 于 工 程 计 划 协 调 工 程 进 展

项 目 经 理 将 负 责 收 集 有 关 产 品 到 货、运 输 、开 箱 、现 场 准 备、安 装 进 展、 用 户 技术 人 员 反 应 、 等 有 关 工 程 信 息。 在 分 析 所 有 有 关 信 息 之 后， 如 果 认 为 某 些 因 素 会 导 致 工 程 进 展中 止 或 延 迟， 项 目 经 理 将 负 责 采 取 必 要 的 措 施 。 项 目 经 理 将 全 权 负 责 工 程 进 展 的 督 导 和 调 整 以确 保 整 个 工 程 的 全 面 完 成。

### C 、工 程 管 理

项 目 经 理 将 召 集 技 术 工 程 师， 以 形 成一 个 详 细 的 工程 管 理 计 划。 在 得 到 用 户 有 关 方 面 的 同 意 之 后， 项 目 经 理 将 组 织 有 效 的 人 力 资 源 完 成 工 程 实 施技 术 资 料、 并 对 具 体 细 节 加 以 修 正。

### D 、人 力 资 源 和 设 备 资 源 的 统 一 管 理

项 目 经 理 将 负 责 对 工 程 实 施 中 所 有 人 力 资 源、设 备资 源、测 试 仪 器 资 源 进 行 统 一 调 配。

### E 、统 一 协 调

项 目 经 理 将 做 为 XX 公 司 方 面 负 责 统 一 协 调 双 方的 工 程 合 作 关 系 的 代 表 ( 用 户、用 户 下 属 设 备 安 装 地 机 构、 XX 公 司) 在 必 要 时， 项  目 经 理 将 向  用 户 提 出 召 集 项 目 工 程 讨 论 会 的 请 求。

## 3 、工 程 管 理 计划 (PMP)

在 整 个 工 程 实 施 中， 会 遇 到 许 多 大 范 围 的、 有 关 交 叉 相 关 的 工 程 技 术 问 题， XX 公 司 将 采 用 有 效 的 措 施 以 确 保 所 有 交 叉 相 关 细 节 在 设 备 进 行 现 场 安 装 和 割 接 以 前 进 行 预 处理。 这 种 工 作 程 序 将 取 决 于 工 程 管 理 计 划 文 件 的 准 确 性 和 详 细 性。 该 计 划 是 在 项 目 经 理 和 有 关技 术 工 程 师 对 工 程 细 节 进 行 详 细 研 究、 对 所 有安 装 现 场 进 行 详 细 调 查 之 后 所 产 生 的 关 键 性 技 术文 件。 工 程 管 理 计 划 包 括 以 下 内 容：

-          网 络 拓 扑 结 构；

-          网 络 全 网 IP 规 划 表；

-          语 音 ， 及 VPN 规 划 ；

-          中 心  设 备 热 备 份 规 划 ；

-          项 目 实 施 计 划 表；

-          机 房 环 境 要 求 表

-          节 点 机 柜 布 置 和 布 缆 需 求 详 细 说 明；

-          用 户 通 信 线 路 说 明；

-          详 细 割 接 计 划；

-          根 据 用 户 具 体 技 术 需 求 进 行 软 件 参 数 设 定 的 技 术 说 明。

该 工 程 管 理 计 划 书 将 始 终 贯 彻 于 整 个 工 程 实 施 过程 之 中， 并 且 是 整 个 工 程 实 施 的 基 本 技 术 文 件。 按 照 该 文 件 的 精 神 和 具 体 内 容 对 整 个 工 程 中 各个 具 体 工 程 细 节 进 行 微 调 以 确 保 整 个 工 程 能 够 顺 利、 按 时 完 成。 XX 公 司 通 过 在 中 国 进 行 多 业 务网 络 工 程 实 施 的 实 践 证 明， 该 工 程 管 理 计 划 书 对 网 络 工 程 的 实 施 具 有 非 常 重 要 的 作 用。 负 责 各安 装 地 设 备 安 装、 调 试 的 XX 公 司 各 地 办 事 处 的 工 程 师 可 以 根 据 该 技 术 文 件 的 内 容 基 于 具 体 情况 灵 活 处 理 各 类 技 术 问 题， 但 又 可 以 确 保 整 个 工 程 实 施 的 整 体 性。

## 4 、工 程 协 调 会

由 于 工 期 较 紧， 而 且 工 程 覆 盖 范 围 较 大 ， 所 以 工程 能 否 顺 利 实 施 的 一 个 重 要 因 素 是 用 户、 用 户 下 属 安 装 地 机 构 的 工 程 管 理 人 员、 以 及 XX 公 司 各方 面 进 行 合 作 的 密 切 性 和 一 致 性。 相 互 之 间 的 合  作 和 理 解 是工 程 实 施 成 功 的 另 一 个 重 要 基 石。 通 过 工程 协 调 会的 方 式 可 以 为 参 与 用 户 业 务数 据 网 工 程 的 各 个 有 关 方 面 有 机 会 面 对 面 地 交 流 各 自 负 责 工 作 的 进 展 状 况 。 为 了 确 保 整 个 工程 的 顺 利 实 施， 我 们 衷 心 希 望 用户 有 关 方面 的 负 责 人 员 能 够 对 工 程 协调 会 提 供 有利 的 支 持， 并 且能 够出 席 工 程重 要 阶 段 的 工 程 协 调 会 议。 以 便XX 科 技有 限 公 司 能够 通 过 该 工 程 协调 会 向 用户 有 关 方 面 提出 需 要协 调 和 帮助 的 请 求。

每 次 的工 程 协 调会 都 会 形 成《协 调 会 议纪 要》， 项 目 实施过 程 中 所 遇 到 的 问 题， 项 目 经 理 根 据 《协 调 会议 纪 要》 进 行 事 物 处 理。

## 5、文 档 管 理

在 整 个 工 程 的 实 施 过 程 中， 因 数 据 网 络 的 建 设 通 常 与 系 统 集 成 公 司、 传 输单 位 等 进 行 多 方位 配 合， 交 互 期 间 产 生 的 文 档 必 须 进 行 规 范 化 管 理。 XX 公 司 将 针对 项 目 成 立 文 档管 理 小 组， 由 指 定 人 员 负 责  该 项 目 产 生 的一 系 列 文 档， 并 建 议 用 户 方 也 指 定 人 员 进 行 文 件 的 管 理。

项 目 实 施 中， 将 会产 生 以 下 文 件：

1、 网 络 项 目 技 术 应 答 书

2、 到 货 设 备 验 收 单

3、 项 目 开 工 协 调 会 会 议 纪 要

4、 项 目 实 施 计 划 表

5、 机 房 环 境 要 求 表

6、 用 户 通 信 线 路 调 查 表

7、 项 目 实 施 日 志

8、 用 户 需 求 更 改 记 录

9、 网 络 方 案 全 网 IP 规 划 表

10、网 络 方 案 拓 扑 图

11、项 目 初 验 报 告

12、项 目 终 验 报 告

13、设 备 配 置 资 料

以 及 其 他 在 项 目 实 施 过 程 中 产 生 的 相 关 文 件。

# 第 二 章、 工 程 实 施

整 个 工 程 将 分 为 四 个 阶 段：

第 一 阶 段： 工 程 准 备 阶 段

第 二 阶 段： 硬 件 安 装 联 调 阶 段

第 三 阶 段： 工 程 初 验

第 四 阶 段： 试 运 行 及 终 验

## 第 一 阶 段： 工 程 准 备 阶 段

工 程 准 备 阶 段为 合 同 签 定 后 展 开。 在 此 期 间， 双 方工 程 人 员 见 面， 了 解 人 员 配 备 情 况， 做 好 调研 及 整 体 规 划， 具 体来 说 必 需 做 好 如 下 准 备 工 作 ：

-         合 同 双 方 建 立 一 个 高 效 运 作 的 工 程 管 理 体 系（ 管 理 队  伍 及 协 商 机 制）

-         网 络 整 体 规 划， 包 括 IP 地 址 规 划、 路 由 规划

-         对 甲 方 人 员 的 培 训

-         机 房 环  境 的 准 备

-         通 讯 线 路 的 准 备

## 第 二 阶 段： 硬 件 安 装 联 调 阶 段

硬 件 联 调 阶 段 为 所 有 合 同 设 备 到 达 合 同 所 定 交 货 地 点 后 随 即 展 开。 在 本 阶段， 应 确 定 安 装 工 作 的  进 度 ， 解 决 安  装 过 程中 出 现 的 问 题， 确 定 验  收 的 方 法 和 步 骤。 具 体 应 做 好 如 下 工 作：

-         设 备 到 货 后 的 验 收 工 作

-         网 络 设 备 的 安 装 调 试

-         主 机 系 统 的 安 装 调 试

-         网 管 软 件 的 安 装

-         安 全 系 统 软 件 的 安 装

-         硬 件 联 调

-         用 户 现 场 培 训

-         双 方 签 定 项 目 现 场 验 收 报 告

## 第 三 阶 段：工 程 初 验

初 验 阶 段 为 硬 件 安 装 联 调 完 成 后 随 即展 开。 将 本 次工 程 需 要 的 应 用 要 求 和 先 期 的 用 户 需 求 进 行 核 实， 先 进 行 分 步 调 试， 再 进 行 整 体 应用 系 统 的 联 调。 测 试 通 过 以  后 进 行 合 同  初 验。 在 此 期 间 ， XX 科 技 公 司 将 按 照 用 户 的 初验 规 范 对 设 备 配 置 和 应 用 环 境 逐 一 落 实 ， 和 用 户 共 同 做 好 如 下 工 作：

-                   良 好 的 调 测 环 境

-                   配 套 齐 全 的文 档

-                   调 测 中 双 方 人 员 的 紧 密 配 合

## 第 四 阶 段： 试 运 行 及 终 验

在 此 阶 段， 安 装 和 调 试 工 作 已 全 部 完 成， 在 经双 方 认 可 后， 实 施 阶 段 可 转 入 试 运 行 阶 段， 此 过 程， XX 公 司 将 遵 守 合 同 售 后 服 务 条 款 向 用 户 提供 技 术 支 持 和 服 务， 并 开 始 逐 步 移 交 工 程 文 档。

具 体 包 括 以 下 工 作：

### 1．项 目 进 度 表：

| 网 络 项 目 实 施 进 度 表 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 工程进度里程碑 |  |  |  |  | 时间表（以周为单位） |  |  |  |  |  |  |  |
| *月*日签定合同 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 。。。 |
| 合同生效 |  |  |  |  |  |  |  |  |  |  |  |  |
| 双方负责人协商人 员配置、总体安排 |  |  |  |  |  |  |  |  |  |  |  |  |
| 双方落实人员安排 |  |  |  |  |  |  |  |  |  |  |  |  |
| 提 交 设 备 安 装环境需求报告 |  |  |  |  |  |  |  |  |  |  |  |  |
| 提 交 工 程管 理 计 划 |  |  |  |  |  |  |  |  |  |  |  |  |
| 需求分析 |  |  |  |  |  |  |  |  |  |  |  |  |
| IP规划、路由规划 |  |  |  |  |  |  |  |  |  |  |  |  |
| 系统总体功能设计 |  |  |  |  |  |  |  |  |  |  |  |  |
| 甲方人员培训 （网络） |  |  |  |  |  |  |  |  |  |  |  |  |
| 设备到货期 |  |  |  |  |  |  |  |  |  |  |  |  |
| 设备安装环境验收 (机房、线路） |  |  |  |  |  |  |  |  |  |  |  |  |
| 设备现场安装、测 试 |  |  |  |  |  |  |  |  |  |  |  |  |
| 提交网络系统初验 程序 |  |  |  |  |  |  |  |  |  |  |  |  |
| 网络、主机初验 |  |  |  |  |  |  |  |  |  |  |  |  |
| 系统初验 |  |  |  |  |  |  |  |  |  |  |  |  |
| 试 运 行 |  |  |  |  |  |  |  |  |  |  |  |  |
| 系统终验 |  |  |  |  |  |  |  |  |  |  |  |  |

### 2．准 备 工 作 要 求

由 XX 公 司 提 供 网 络 设 备 的 体 积、 重 量、 耗电 量 等 规 格， 要 求 作 好 机 房 的 布 线、 电 源 等配 套 准 备 工 作。 在 具 体 工 作 展 开之 前， 由 XX 公 司 提 供 机房 环 境 要 求 及 通 信 线 路 调 查 表， 要 求 建 设方 给 予 确 认。

### 3．网 络 拓 扑 结 构

XX 公 司 根 据 网 络 设 计 方 案， 对 每 一个 地 州 的 网络 建 设， 提 交 网 络 拓 扑 图， 对 于 具 体 工 程 实 施 过 程 中 发 生 的 变 更 ， 新  时 公 司 作  出 详 细 记 录， 并 及 时 与 建 设 方 协 调。

全 网 拓 扑 结 构 如下 ：

### 4、网 络 设 备 命 名规 则

在 云 南 省 绿 卡 INTRANET 网 络 中 所 有 设 备 遵 循  统 一 的 命 名 方 式： A-BC。 A 为  地 州 名， B 为 设 备 类 型， C 为 设 备 型 号 及 编 号。

例 如：玉 溪 中 心 核 心 路 由 器 7513 在 网 络 中 命 名 为 YuXi-r7513-01; 文 山  州 交 换 机  Catalyst 1924 在 网 络 中 命 名 为 wenshang-s2924-01。

### 5．线 路 情 况 说 明

由 于本 网 作 为 全 省 邮 政 绿 卡 及 综 合 业 务 的 基 础 数 据 传 输 平 台 ， 数 据 流 量 大 ， 安 全 可 靠 性 较 高 ， 因此 全 省 的 三 个 中 心 互 连 至 各 地 州 广 域 网 线 路 采 用 2 个 2 M 线 路 ， 平 时 负 载 均 担 ， 当 一 条 线 路故 障 时 ， 仍 然 可 由 另 一 条 线 路 传 输 ， 以 待 故 障 恢 复 。 地 州 至 各 县 团 分 局 根 据 数 据 流 量 大 小 的不 同 ， 对 于 数 据 量 大 的 采 用 2 M / 1 2 8 k ， 数 据 量 小 的 采用 1 个 6 4 M 。 同 时 采 用 P S T N 作 为 备 份 链 路 。

### 6 、 地 址 分 配

云 南 省 绿 卡 及 邮 政 网 络 IP 地 址 分 配 由 国 家 邮 政总 局 规 划 并 制 定 分 配 原  所 有 IP 地 址 已 分配 完 成 。

每 个 地 州 都 拥 有  B 类 地 址， 在 目 前 的 云 南 邮 政 应 用 中， 已 启 用 或 备 用 的 IP 地 址 如 下：

1，绿 卡 网  IP 地 址

2，邮 政 综 合 网 预 留 IP 地 址

在 YNLK 网 络 的 网 络 工程 中 ， 考 虑 到 网 络 为 初 建 所 以 预 留 的 IP 比 较 多 ， 可 以 规 划 的 比 较 细 致 ， 考 虑 的 目 前 仅 有 部 分应 用 在 网 络 上 运 行 ； 作 为 邮 政 应 用 的 网 络 基 础 平 台 ， 本 次 I P 地 址 分 配 充 分 考 虑 日 后 应 用 的扩 展 性 ； 本 次 I P 地 址 的 分 配 采 用 连 续 的 I P 网 络 号 ， 便 于 网 络 作 路 由 汇 聚 ； 本 次 I P 地 址采 用 可 变 长 子 网 掩 码 （ V L S M ） 来 细 化 子 网 ， 以 节 约 I P 资 源 。

I P 分 配 原 则 ：

保 持 邮 政 总 局 规 划分 配 的 应 用 I P 分 配 方 案 不 变 ；

在 各 地 州 的 I P 地 址 范 围 上 ， 本 次 所 分 I P 从 1 0 0 向 后 依 次 类 推 ， 并 考 虑 使 用 V L S M 。

在 各 地 州 的 I P 地 址 范 围 上， 启 用 所 属 I P 范 围 的 最 后 2 个 子 网 作 为 地 州 到 下 属 县 、 团 的 W A N 互 连 地 址 。

在 各 地 州 的 I P 地 址 范 围 上 ， 启 用 所 属 I P 范 围 的 2 5 3 网 段 作 为 网 络 设 备 的 LOOPBACK 地 址 。

对 于 每 个 地 州 ， 每 个 应 用 占 用 1 个 C。

对 于 每 个 县 局 ， 各 项 应 用 在 4 个 C 中 进 行 分 配 。

对 于 每 个 储 蓄 所 ， 各 项 应 用 在 1/2 个 C 中 进 行 分配 。

剩 余 IP 子 网和 xxx.224.254.X/30 作 为 WAN 互 联 备 用 IP 地 址 。

地 州 各 网 络 应 用 IP 地 址的 分 配 ：

地 州 各 网 络 新 增 应 用 的 范 围 从 X.X.100.X  向 后 开 始 启 用 IP 地 址 。 原 有 IP 地 址 维 持 不 变 。 每 个 应 用 对 应 1 个 C 类 ， 最大 主 机 数 < 254。

如：玉 溪 可用的IP地址范围为X.X.100.0/24  --à向后对应。

各中 心 和 各 州 、 县 市 的WAN互联IP地址分配：

|  | 局名 | WAN主链路 | WAN 第二链路 |
| --- | --- | --- | --- |
| 至 | 昆 明 | 151.240．20．5/30 | 151.240．20．105/30 |
|  | 大 理 | 151.240．20．9/30 | 151.240．20．109/30 |
|  | 玉 溪 | 151.240．20．13/30 | 151.240．20．113/30 |
|  | 曲 靖 | 151.240．20．17/30 | 151.240．20．117/30 |
|  | 红 河 | 151.240．20．21/30 | 151.240．20．121/30 |
|  | 楚 雄 | 151.240．20．25/30 | 151.240．20．125/30 |
|  | 丽 江 | 151.240．20．29/30 | 151.240．20．129/30 |
|  | 迪 庆 | 151.240．20．33/30 | 151.240．20．133/30 |
|  | 临 沧 | 151.240．20．37/30 | 151.240．20．137/30 |
|  | 保 山 | 151.240．20．41/30 | 151.240．20．141/30 |
|  | 昭 通 | 151.240．20．45/30 | 151.240．20．145/30 |
|  | 施 茅 | 151.240．20．49/30 | 151.240．20．149/30 |
|  | 怒 江 | 151.240．20．53/30 | 151.240．20．153/30 |
|  | 版 纳 | 151.240．20．57/30 | 151.240．20．157/30 |
|  | 德 宏 | 151.240．20．61/30 | 151.240．20．161/30 |

### 7．路 由 规 划

● 路 由 协 议 的 选 择

当 前 主 要 的 动 态 路 由 协 议 有 RIP、 IGRP、 EIGRP 以 及 OSPF。在 工 程 实 施 中 ， 选 用 OSPF 协 议 。 在 每 个 HOP 上 都 定 义 了 一 个 COST， OSPF 认 为 最 优 化 的路 径 为 最 好。

●  网 络 结构 及 自 制 域  (AS) 设 置

云 南 省 绿 卡 INTRANET 网 络 以 为 全 网 的 系 统 中 心， 全 网 的 15 个 地州 通 过 1 个 64k DDN 与 中 心 相 连。

云 南 省 绿 卡 INTRANET 网 内 采 用 OSPF 动 态 路 由 协 议。 OSPF 协 议 采 用 多 区 (AREA) 模 式， 具 有 较 好的 扩 展 性 ， 而 且 区 内 的 错 误 路 由 不 会 影 响 全 网， 大 大 增加 了网 络的 可 靠 性。 所 有 地 州 的 主路 由 器 与 省 中 心 路由 器 都 划 分到 OSPF 的 Area 0 内， 与 之 相 连 的 下 级节点 的 设 备 再 分别 划 为 不 同的 EIGRP Area。 这 将 最 大 限 度地 利 用 OSPF 的 分 区 管 理 优 势。

云 南 省 绿 卡 INTRANET 网 络  域 的 划 分：

| 序号 | 地区名称 | 区域号 |
| --- | --- | --- |
| 0 | 省中心 | AREA 0 |
| 1 | 昆 明 | AREA 11 |
| 2 | 大 理 | AREA 12 |
| 3 | 玉 溪 | AREA 13 |
| 4 | 曲 靖 | AREA 14 |
| 5 | 红 河 | AREA 15 |
| 6 | 楚 雄 | AREA 16 |
| 7 | 丽 江 | AREA 17 |
| 8 | 迪 庆 | AREA 18 |
| 9 | 临 沧 | AREA 19 |
| 10 | 保 山 | AREA 20 |
| 11 | 昭 通 | AREA 21 |
| 12 | 思 茅 | AREA 22 |
| 13 | 怒 江 | AREA 23 |
| 14 | 版 纳 | AREA 24 |
| 15 | 德 宏 | AREA 25 |
| 16 | 文 山 | AREA 26 |

●  路 由 汇 聚

地 州 到 省 中 心 的 路 由 汇 聚：

在 IP 地 址 的 规 划 时 已 经 考 虑 到 路 由 汇 聚 ， 建 议 每 个 地 州 应 分 配 两 个 连 续 的 B 类 地 址 ， 以 便 可 以 汇 聚 成 一 条 路 由 信 息 向 其 他 区 域 传 送 。 通 过 对 O S P F 的 适 当 配 置 ， 可 以 对 地 州 的 路 由 信 息 进 行 汇 总 。 各 地 州 的 核 心 路 由 器 作 为 区 域 边 界 路 由 器 ABR ， 可 以 把 进 入 一 个 区 域 的 各 县市 分 局 的 多 条 路 由 减 少 到 一 条 路 由 。

例 如 对 大 理 在 其 核 心 路 由 器 上 可 进 行 如 下 配 置 ， 使 其 汇 总 成 一 条 信 息 ：

router ospf 991

network  151.240．0．0.0.0.255 area12

● 负 载 均 担

OSPF 路 由 协 议 可 根 据 两 条 传 输 线 路 ， 作 到 流 量 的 负 载 分 担 。

● 从 EIGRP 向 OSPF 转 换 的 路 由 系 统 割 接

由 于 云 南 省 绿 卡 一 期 建 设 采 用 的 路 由 协 议 为 EIGR ， 本 期 建 设 需 要 OSPF 协 议 ， 在 系 统 割 接中 要 考 虑 到 路 由 的 正 确 、 完 整 统 一 ， 不 会 引 起 网 络 通 讯 的 严 重 事 故 。 具 体 考 虑 如 下 ：

首 先 在 省 中 心 路 由 器 上 运 行 以 上 两 种 路 由 协 议 ， 相 互 之 间 进 行 路 由 信 息 的 转 发 ， 既 保 证 以 前 路 由 协 议 的 运 行 ， 又 为 后 续 各 地 州 使 用 新 的 路 由 协 议 作 好 准 备 。 随 后 在 进 行 地 州 、 县 市 的 设 备 安 装 时 使 用 OSPF 协 议 ， 通 过 路 由 汇 总 将 本 地 的 路 由 信 息 传 送 至 省 中 心 ， 再 通 过 路 由 转 发 与 全 省 的 网 络 保 持 路 由 畅 通 。 待 全 部 安 装 完 成 后 ， OSPF 已 全 部 配 置 完 成 ， 可 将 一 期 所 用 EIGRP 配 置 从 各 路 由 器 中 删 除 。

# 8.	云南绿卡网络的具体技术特性，可靠性、冗余备份

# 8.1	可 靠 性、 冗 余 备 份

网 络 系 统 的 冗 余 可 靠 性 如 何， 是 关系 到 整 个 绿 卡 网 络 能 否 正 常 运 行 的 关 键 ， 我们 通 过 硬 件、 软 件、 线 路 设 施 以 及 各 个 层 次 来 实 现 绿 卡 网 络 系 统 的 高 可 靠 性。

## 8.1.1、  路 由 器 冗 余 备 份

为 了 防 止 网 络 系 统 出 现 单 点 故 障，采用 了 双 路 由 器 以 实 施 网 络 关 键 设 备 的 冗 余 备 份。 在 本 方 案 中 当 主 路 由 器 Cisco7513出 现 故 障 时, 远 程 的 路 由 器 Cisco 2611 将 触 发拨 号 线 路 到 中 心 的 访 问  服 务器AS5300, 这 样路 由 器 Cisco7513 和 访 问  服 务器AS5300 就作 相  互 备 份。

8.1.2、 路 由 的 备 份

在 整 个 网 络 中 ， 主 要 路 由 都 有 备 份，主 路由 器 Cisco7513 和 访 问 服 务器 AS5300 到 中 心 交 换 机 Catalyst 3200 都 有路 由 备 份， 在 此 方 案 中， 用Cisco 的 IRB 技 术 可 以 实 现 路 由 备 份。 Cisco7513 和 AS5300 均 有 两 个以 太 口 分 别 连 到 不 同 的 中 心 交 换 机 Catalyst 3200， 从 Cisco7513、 AS5300 到 主 机 就 有 两 条 线路 存 在， 正 常 运 行 时 只 有 一 条 线 路 工 作， 如 果 这 条 线 路 出 现 故 障， 就 会 切 换 到 另 外 一 条 线 路， 主机 不 用 做 任 何 路 由 修 改，同 时 由 于 切 换 时 间 非 常 短， 用 户 应 用 (TCP 连 接)  不 会 受 到 中 断， 保 证 了 绿 卡 网 络 系 统 关 键 业 务 的 正 常 运 行。

8.1.3、 广 域 网 线路 冗 余 备 份

在 网 络 系 统 的 冗 余 设 计 方 案 中，WAN 线 路 的 冗 余 备 份 是 十 分 重 要 的， 在 绿 卡 网 络 方案 中， 各 地 区 节 点 到 中 心 的 广 域 连 接 都 采 用 了 双 WAN 线 路， 主 线 路 用64K DDN ， 备 份线 路 用 PSTN ，以 防 止 线 路 故 障。

在 实 施 冗 余 WAN 线 路 连 接 时，  可 以 自 动 进 行 线 路 的 切 换 以 及 路 由 的 及 时 更 新。

我 们 设 计 使 用 OSPF (Open Shortest Path First) 开放 性 最 短 路 径 优 先 这 一 先 进 的 动 态 路 由 协 议 ，在 网 络 状 态 变 化 时 实 现 最 佳 路 径 的  重 新 计 算。

OSPF 是 一 种 链 路 状 态 路 由 协 议， 它能 在 网 络 链 路 状 态 发 生 变 化 时， 根 据 新 的 网 络 链 路 状 态 数 据 库 立 即 重 新 计 算 最 佳 路 由， 从 而 使得 我 们 网 络 主WAN 线 路 断 掉 后， 备 份 WAN  线路 能 迅 速 被 OSPF  路 由 进 程  计 算 出 来， 已 保 证 绿 卡  业 务  被 中 断。

# 8.2.	性 能 优 化 设 计

为 了 给 绿 卡 网 络 系 统 提 供 高 性 能 的 网 络 平 台， 我 们 通 过 一 系 列优 化 设 计 和 配 置， 来 实 现 减 小 网 络 负 载、 快 速 收 敛 路 由 以 及 对 绿 卡 业 务 应 用 网 络 流 进 行 优 先 排队。

## 8.2.1、 路 由 性 能 优 化

我 们 利 用 OSPF 路 由 协 议 层 次 化 的路 由 思 想， 将 整 个 绿 卡 系 统 网 络 分 成 多 个 小 的 OSPF  区 域 AREA,  区 域 内部 的 路 由 只 在 本 区 域 内 传 送， 这 样 可 以 减 少 WAN 上 的 网 络 流 量。 同 时， 各 个 区 域 内 的 路 由 器 较 少，区 域 内 部 的 路 由 的 计 算 非 常 快， 这 样 减 小 对 路 由 器 CPU 和 内 存 的 使 用， 使 得 路 由 器 的 处 理 效 率更 高。

另 外， 我 们 还 利 用 VLSM 可 变 长 度 子网 掩 码 做 IP 地 址 分 配 结 合 OSPF 路 由 总 结 的 特 性， 将 大 量 的 路 由 信 息 缩 减 到 一 条， 可 以 减 小 网络 负 载 以 及 加 快 路 由 速 率。

## 8.2.2、 业 务 性 能 优 化

为 了 保 证 绿 卡 业 务 的 优 先 地 位， 我们 可 以 利 用 优 先 级 队 列 Priority-Queuing  来 为 绿 卡 业 务 应 用 设 置 最 高 的 优 先 级 别， 使 得 绿 卡 业 务 的 数 据 流 能 得 到 路 由 器 的 优 先处 理， 从 而 保 证 了 绿 卡 业 务 性 能 的 快 速 高 效。

# 8.3.  安 全 管 理 设 计

关 键 业 务 网 络 中 安 全 控 制 和 可 管 理性 是 非 常 重 要 的， 我 们 通 过 下 面 一 些 方 法 来 实 现 对 网 络 的 安 全 控 制 和 管 理。

## 8.3.1、 访 问 控 制 列 表

通 过 在 路 由 器 上 设 置访 问 控 制 列 表 Access-list, 可 以 对 网 络 访 问 进 行 安 全 控 制， 如 限 定 访 问 者 的 范 围( 指 定IP 地 址范 围)， 可 以 访 问 的 资 源( 主IP 地 址), 以 及 使 用 的 协 议(Telnet,FTP,HTTP 等， 即 端 口 号)。

## 8.3.2、 AAA 认 证、 授 权 及 记 帐 机 制

Cisco 的 AAA ( Authentication , Authorization , Accounting) ， 提 供 了 一 套 完 整 的  机 制 来 实 现  对 用 户 访 问 控 制， 它 提 供 了 业 界 标 准 的 安 全 认 证 协 议， 如PAP,CHAP,TACACS+,RADIUS,。并 且 可 以 和 UNIX 操 作 系 统 /etc/password 或 Windows NT的 用 户 管 理 结 合 起 来， 为 网 络 中的 多 台 设 备 提 供 访 问 控 制。

# 第 三 章、 技 术 支 持 与服 务

在 一 个 大 型 网 络 建 成 并 投 入 运 行 后， 受 外 部 环 境 和 内 部 组 织 结 构、 应 用 需求 等 变 化 的 影 响， 不 可 避 免 地 会 产生 某 些 问 题。 为 了 使 客 户 拥 有一 个 健 康 的 系 统， XX 公 司 将 为客 户 提 供全 面 的技 术 支持 和 服 务。

## 1、技 术 支 持 力 量

XX 公 司 在 成 都 设 有 专 门 的 技 术 支 持 中 心 ， 向 用 户 提 供 技 术 咨 询 ， 故 障 诊 断 ， 排 除 故 障 等 全 面 技 术 支 持 。

XX 公 司 在 全 国 各 地 设 有 办 事 处 ， 有 经 验 丰 富 的 工 程 师 队 伍 ， 向 全 国 各 地 提 供 本 地 化 的 技 术 支 持 ， 保 证 实 时 性 。

支 持 方 式

在 一 般 情 况 下 ， 用 户 通 过 电 话 、 电 子 邮 件 和 传 真 等 方 式 ， 将 所 遇 到 的 问 题 报 告 给 技 术 支 持 中 心 或 本 地 办 事 处 。 所 有 电 话 、 电 子 邮 件 、 传 真 都 将 被 记 录 、 备 案 并 跟 随 问 题 的 全 过 程 。

## 2、售 后 服 务

XX 公 司将 充 分发 挥 各 办事 处 的技 术 支 持 能 力， 能 及 时为 用 户 解决 问 题， 提 供全 面 的 工 程 和 技 术 支 持。 基 于 本 地 化 的 技 术 服 务 队 伍 能 够 保 证 在 第一 时 间 内 以 多 种 手 段 对 最 终用 户作 出 反 应。

1、 指 导 性 响 应

当 系 统 发 生 问 题 时， 首 先 由 客 户方 面 的 工程 技 术 人 员对 故 障 现 象 进 行 详 细 的 观 察 记 录， 然 后通 过 各 种 通 讯 手段 将 情 况通 知 XX公 司 ， 由 XX公 司 的 工程 技 术 人员 进 行 诊 断， 确 认合 适 的 解 决 办 法， 然 后再 指 导 客户 的 工程 技 术人 员 进行 现 场 操 作。

2、 远 程 响 应

当 系 统 发 生 问 题 时， 首 先 由客 户 方 面的 工 程 技 术人 员 对 故 障 现 象 通 过 各 种 通 讯手 段 将 情况 通 知 XX 公 司， 由 XX 公 司 的 工 程 技术 人 员 通 过 MODEM 或 其 他 远 程连 接 手段 介 入 用 户的 网 络 系 统， 利 用 SNMP， RMON 等 相 应的 网 络 管 理机 制 对 网 络 进行 诊 断， 确 认 合 适的 解 决 办 法， 进 行 远 程 操 作。

## 3、保 修 服 务

XX 公 司 对合 同 中 的 CISCO 设 备 提 供 三 年 的 免 费 保 修 更 换 服 务， 保 修 期 自 验 货 合 格 之 日 起 计 算。 在 保 修 期 内 如 设 备由 于 本身 质 量 原 因  而 出 现 故 障， 用 户应 立 即 通 知 XX  公 司， XX 公 司 在 接到 用 户 的  通 知 后， 将 在 最 短 的 时 间 内 完 成 设 备 的 返 修。

## 4、技 术 支 持 服 务 时 间 及 人 员

XX 公 司 在 成 都、 昆 明 设 有 技 术 支 持 热 线， 为 用 户 提 供 7 X 24 小 时 的 技 术 支 持。 专 家 支 持 队伍 拥 有 多名 在 应 用系 统、 数 据通 讯 领 域、 网 络安 全 领 域 的资 深 专 家， 随 时对 XX 公司 参 与 建设 的 项 目 进 行 追 踪 和 检 查。

在 云 南 省 绿 卡 网 络 的 建 设 中， XX 提 供以 下 技 术 人 员作 为 此 项 目 的 技 术 支 持：

# 第 四 章、 网 络 设 备 安 装

## 1、云 南 省 绿 卡 工 程中 心 安 装 实 施

现 有 网 络 中 心 位 于 昆 明 市 邮 电 管 理 局 ， 在 本 期 网 络 的 扩 容 改造 工 程 中， 工 程 实 施 中 上 可 分 为 两 个 阶 段 ：

将 新 增 中 心  网 络 设 备:Cisco router 7513 壹 台 、 Cisco router 3640 壹台 、 CiscoAs5300 壹 台、 Catalyst 3200  两 台 。

| 序号 | 设备 | 设备描述 | 数量 |
| --- | --- | --- | --- |
| 一、 | 核心路由器7513 |  | 1 |
| 二、 | 中 心 交换机 3200 |  | 2 |
| 三 、 | 语 音 网 关 AS5300 |  | 1 |
| 四 、 | 语 音 路 由 器 3640 |  | 1 |

## 2、电 路 情 况 调 查 表

省中心与各地州64K线路情况调查表：

| 序号 | 名称 | 电路情况 | 备注 |
| --- | --- | --- | --- |
| 1 | 昆 明 | □ |  |
| 2 | 大 理 | □ |  |
| 3 | 玉 溪 | □ |  |
| 4 | 曲 靖 | □ |  |
| 5 | 红 河 | □ |  |
| 6 | 楚 雄 | □ |  |
| 7 | 丽 江 | □ |  |
| 8 | 迪 庆 | □ |  |
| 9 | 临 沧 | □ |  |
| 10 | 保 山 | □ |  |
| 11 | 昭 通 | □ |  |
| 12 | 思 茅 | □ |  |
| 13 | 怒 江 | □ |  |
| 14 | 版 纳 | □ |  |
| 15 | 德 宏 | □ |  |

## 3 、 机 房 情 况 调 查 表：

| 序号 | 调 查 项 | 正常 | 备注 |
| --- | --- | --- | --- |
| 1 | 布线工程 | □ |  |
| 2 | 电源 | □ |  |
| 3 | 机房温度 | □ | 0-40 |
| 4 | 机房湿度 | □ |  |

## 4、大 理 、 玉 溪 中 心 LAN 的 调 整

A、将 中 心 交 换 机 调 整 为 Catalyst3200， Catalyst3200 通 过 快 速 以 太 网 连 接 至 大 理 、 玉 溪 中 心 路 由 器 CISCO7513。 不 同 的 应 用 通 过 V L A N 连 接 到 Catalyst3200 的 相 应 端 口 ，对 Catalyst3200 的 端 口 分 配 作 出 规 划 如 下 ：

Catalyst 3200端口分配表：

| 模块/端口 | 型号/VLAN ID | 说明/应用 | 对应7507子接口 | 备注 |
| --- | --- | --- | --- | --- |
| 模块1 | WS-X3010 |  |  |  |
| 模块2 | WS-X3010 | 4端口10M模块 |  |  |
| 模块3 | WS-X3010 |  |  |  |
| 模块4 | WS-X3002 | 4端口100M模块 |  |  |
| 2/1端口 | TRUNK |  |  | 100M |

B、 中 心 7513 的 调 整

物 理 模 块 的 调 整

中 心 至 各 地 州 的 线 路 由 64K + DDN ， 相 应 模 块 （ PA-4E1G/75=） 共 3 块 ， 在 做 配 置 前 ， 需 将 新 增 模 块 及 V I P 模 板 安 装 在 7513 合 适 的 插 槽 内。

将 转 换 器 正 确 的 连 接 到 7513 各 端 口 ， 将 连 至 地 州 的 PCM 2M 线 路 做 上 标 签 ， 并 正 确 连 接 到 转 换 器 上 。

## 5 、 地 州 、 县 局 的 安 装

1、 地 州 节 点 设 备 连 接 说 明

使 用 设 备 ： CISCO2611

线 路 情 况 ： 128K +DDN

应 用 连 接 方 式 ：SECONDARY 、 共 享 10M 带 宽 、 无 VLAN 划 分 能 力

县 、 分 局 未 覆 盖 或 未 完 全 覆 盖

2 、 地 州 至 县 、 分 局 的 电 路 情 况 调 查 ， 地 州 机 房 调 查 ， 县 机 房 调 查

2．1 机 房 情 况 调 查 表 ：

| 序号 | 调 查 项 | 正常 | 备注 |
| --- | --- | --- | --- |
| 1 | 布线工程 | □ |  |
| 2 | 电源 | □ |  |
| 3 | 机房温度 | □ | 0-40 |
| 4 | 机房湿度 | □ |  |

设 备 加 电 检 测

检 查 内 存 、 FLASH 、IOS 版 本 等 信 息 ， 并 做 记 录

| 地州名 | 设备名 | 内存 | FLASH | IOS版本 | S/N | 放 置 位 置 |
| --- | --- | --- | --- | --- | --- | --- |
| 红河 | Cisco 2611 |  |  |  |  | 中心机房 |
| 文山 | Cisco 2611 |  |  |  |  | 中心机房 |
| 。。。 |  |  |  |  |  |  |

# 第 五 章 、 工 程 实 施 验 收

## (1)、 数 据 网 络 的 连 通 性 测 试

1）局 域 网 的 连 通 性 测 试

在 云 南 省 邮 政 局绿 卡 工 程 昆 明 中 心 的 任 一 台 计 算 机 上 ping 省 局 上 的 所 有 路 由 器 、 交 换 机 、 服 务 器 、 工 作 站 、 PC ， 均 能 ping 通 ， 说 明 省 局 昆 明 中 心 局 域 网 的 连 通 性。

在 大 理 分 中 心 的 任 一  台 计 算 机 上 ping 大 理 邮 政 局 绿 卡 工 程 网 络 上 的  所 有 路 由 器 、 交 换 机 、 服 务 器 、 工 作 站 、 PC ，均 能 ping 通 ， 说 明 大 理 中 心 邮 政 局 中 心 局 域 网 的 连 通 性 。

2） 广 域 网 的 连 通 性 测 试

在 省 邮 政 局 昆 明中 心 网 络 的 任 一 台 计 算 机 上 ping 省 邮 政 局 昆 明 中 心 以 外 的 其 他 中 心  、州 、 市 县 的 所 有 路 由 器 、 交 换 机 、 服 务 器 、 工作 站 、 PC ， 均 能 ping 通 ， 说 明 省邮 政 局 至 其 他 中 心 、 州 、市 县 的 广 域 网 的 连 通 性。

在 大 理 邮 政 局 中心 网 络 的 任一 台 计 算 机 上 ping 大 理 邮 政 局 以 外 的 其 他 中 心 、 州、市 县 及 省 局 昆 明 中 心 的 所 有 路 由 器 、 交 换机 、 服 务 器 、 工 作 站 、 PC ， 均 能 ping 通 ， 说 明 大 理 邮 政 局 中 心 至 其 它 地 方 的 广 域 网 的 连 通性 。

测 试 结 果 ：以 上 三  项 测 试 内 容 均 达 到 要 求 ， 且 速 度  较 快  。

## (2)、 IP 电 话 的 连 通 性 及 效 果 测 试

1)  从 省 邮 政 局 昆 明 中 心 到 其 他 中 心 的 IP 电 话 连 通性、 效 果 。

2)  从 省 邮 政 局 昆 明 中 心 到 其 他 州 、 县 市 的 IP 电 话连 通 性、 效 果 。

2)  从 大 理 邮 政 局 中 心 到 省 局 昆 明 中 心  的 IP  电 话 连 通 性、 效 果  。

3 ) 从 大 理 邮 政局 到 其 他 州 、 县 市 的 IP  电 话 连 通 性、 效 果。

## (3)、 备 份 线 路 、 备 份 路 由 的 测 试

对 备 份 情 况 的 测 试，可 分 为 以 下 几 步 进 行：

1)  断 开 省 局 昆 明 中 心 到 测 试 地 州 DDN ， 测 试 是 否启 动 备 份 线 路、  备 份 路 由， 通 过show ip route、  show interfce、 telnet 、 ping 方 式 来 测 试， 以 及 IP 电 话 是 否 通 。

2) 恢 复 省 局 昆明 中 心 到 测 试 地 州   DDN ， 测 试 是 否从 备 份 线 路、  备 份 路 由 恢 复 到 DDN 及 主  路 由 工 作 状 态 ， 通 过 show ip route、  show interfce、  telnet 、 ping 方 式 来 测 试 。

## 测 试 结 果 ：以 上 测 试 内 容 均 已 到 到 要 求。

## (4)、 网 络 路 由 汇 聚 的 验 收 测 试

对 路 由 汇 聚 情 况 的  测 试，可 按 以 下  进 行：

检 查 网 络 设 备 配 置， 在 省 局 昆 明 中 心 中 心 路 由 器 及 其 他 中 心 的 路 由 器 上， 通 过 show configuration 命 令， 可 看 到 OSPF 的 路 由 配 置 上 的 路 由 汇 聚 命 令； 通 过 网 络 设 备 操 作 命 令 加 以 验证 各 AREA 之 内 的 网 络 路 由 信息 是 否 已 完  成 汇 聚。 在 各 中 心 的 中心 路 由 器 通 过 显 示 路 由 命 令， 确 认 各地 州、 县 市 的 路 由 信 息 是 通 过一 条 汇 总 信 息 到 达 各 中 心。

## (5)、 网 管 系 统 的 功 能 测 试

1） 验 证 网 管 软件 的 安 装 正 常

观 察 网 管 软 件 的 安 装 文 件（.Log 文 件），核 实 是 否 有 错 误 提 示 信 息。

2）验 证 网 管 软 件 的功 能 正 常

网 管 软 件 完 成 后，可 保 证 以 下 功 能：

网 络 拓 扑 图 的 生 成；

网 络 设 备 的 图 形 显 示 （即 CISCO  view）;

网 络 设 备 的 WEB 界 面 管 理 功 能；

交 换 机 流 量 分 析（Traffice Director）

Vlan  拓 扑

第 六 章    工 程 文 档

为 确 保 云 南 省 绿 卡 工 程 INTRANET 网 工 程 的 有 序、 顺 利 实 施； XX 科 技 公 司 将 向 云 南 省 邮 政 管 理 局 提 交 文 档。

1、 安 装 报 告

XX 科 技 有 限 公 司 于 1999 年 1 月 与 云 南 省 邮 电 管 理 局 领 导 一 起 讨 论  作出 云 南 省 邮 电 绿 卡 INTRANET 网 络 方 案 ， 并 于 1999 年 3 月签 订 合 同 。

我 公 司 于 1999 年 3 月 组 建 工 程 实 施小 组 , 其 中 项 目 经 理 ：冯 根 怀 ，  高 级 工 程 咨 询 人 员 CCIE： 寥 昕 ，  技 术 工 程 师：冯 根 怀、 陈 力 、 黄 远 东  。

项 目 领 导 小 组 ：毛 芒 众 、 熊 晓 明

我 公 司 于 工 程 实施 小 组 与 省 邮 电 管 理 局 技 术 人 员在 3 月 份 召 开 多 次 工 程 协 调 会 议 ， 形 成 《协 调 会议 纪 要》， 其 中 包括 机 房 环 境 、 线 路 准 备 、 施 工 进 度 、 IP 电 话 中 继 、 IP 地 址 分 配 等 。

对 省 局 、 地 州 、 县 局 技 术 人 员进 为 期 数 天 的 培 训 ， 培 训 内 容 包 括 ： 网 络 基 础 知 识 、 TCP/IP、 IP 地 址 的 规 划 ， 路 由 器 概 念/ 功 能/原 理  、  交 换 机  概 念/ 功 能/原 理、 路 由 技 术 、 路 由 协 议、 交 换 技 术 、 网 管 技 术 、 语 音 技 术、 路 由 器 /交 换 机 配 置 。

我 公 司 设 备 于 4 月 1 日 运 到 省公 安 厅 ， 并 于 1 、2、 3 日 开 箱、 上 电 进 行 点 货 、验 货 ， 设 备 均 与 合 同 符 合 ， 且 上 电 检 验 均 正 常。

以 下 为 开 箱 验 货 清 单 ：

玉 溪 ：

| 序号 | 设备 | 数 量 | 序 列 号 | 加 电 情 况 | 备 注 |
| --- | --- | --- | --- | --- | --- |
| 一、 | 核心路由器 |  |  |  |  |
| 1 | CISCO7513/4X2(YX) | 1 | 73017404， RSP: 08220494, 08220504 | 正 常 |  |
| 2 | POWER CORD | 2 |  | 正 常 |  |
| 3 | CONSOLE CAB | 1 |  |  |  |
| 4 | MEM-RSP-64M | 2 |  |  |  |
| 5 | VIP2-40 | 2 | 08218848， 09442542 |  |  |
| 6 | FR-WPP75 | 1 | PP248， 99244 |  |  |
| 7 | PA-FE-TX | 2 | 09675742， 09676817 |  |  |
| 8 | PA-2CE1/PRI-75 | 1 | 09731352 |  |  |
| 9 | CAB-E1-BNC | 16 |  |  |  |
| 10 | SF75BS-11.2.12P | 2 |  |  |  |
| 11 | PA-8T-V35 | 1 | 09724529 |  |  |
| 12 | CAB-OCT-V35-MT | 1 |  |  |  |
| 二、 | CATALYST 3200： |  |  |  |  |
| 13 | WS-C3200B | 2 | 8010554, 7460092 | 正 常 |  |
| 14 | POWER CORD | 2 |  |  |  |
| 15 | CONSOLE CAB | 4 |  |  |  |
| 16 | WS-X3010 | 6 | 8110491, 8110306, 8110270, 8110479, 8110290, 8110267 |  |  |
| 17 | WS-X3002 | 2 | 8070016, 8070011 |  |  |
| 18 | 资 料 (套 ) | 2 |  |  |  |
| 三 、 | AS 5300: |  |  |  |  |
| 19 | AS5300 | 1 | AAE98368196, E1 Card:09366096 | 正 常 |  |
| 20 | POWER CORD | 1 |  |  |  |
| 21 | CONSOLE CABLE | 1 |  |  |  |
| 22 | AS53-E1-60DM | 1 | 09361143 |  |  |
| 23 | FR53-MMTL-60 | 1 |  |  |  |
| 24 | MEM-16F-AS53 | 1 |  |  |  |
| 25 | CAB-E1-RJ45BNC | 2 |  |  |  |
| 26 | 资 料 (套 ) | 1 |  |  |  |
| 配 件 ： |  |  |  |  |  |
| 27 | VIP2-40 | 1 | 08218216 |  |  |
| 28 | PA-2CE1/PRI-75 | 1 | 09731319 |  |  |
| 29 | CAB-E1-BNC | 1 |  |  |  |
| 30 | WSX3010 | 1 | 10131755 |  |  |
|  | 网 管 软 件 : |  |  |  |  |
| 31 | CW-4.0-1VV | 1 |  |  |  |
| 32 | 资 料 (套) | 1 |  |  |  |

大 理 ：

| 序号 | 设备 | 数量 | 序 列 号 | 加 电 情 况 | 备 注 |
| --- | --- | --- | --- | --- | --- |
| 一、 | 核心路由器 |  |  |  |  |
| 1 | Cisco7513, 13-Slot, 2 Cybus, 2RSP4, Dual Power Supply | 1 | 73017401,RSP: 08219358, 08217266 | 正 常 |  |
| 2 | POWER CORD | 2 |  |  |  |
| 3 | 资 料 (套 ) | 1 |  |  |  |
| 4 | CONSOLE CAB | 1 |  |  |  |
| 5 | MEM-RSP-64M | 2 |  |  |  |
| 6 | MEM-RSP4-FLC16M | 2 |  |  |  |
| 7 | VIP2-40 | 2 | 08206638, 08218581 |  |  |
| 8 | FR-WPP75 | 1 | PP241, PP282 |  |  |
| 9 | PA-FE-TX | 2 | 09676128, 09673765 |  |  |
| 10 | PA-2CE1/PRI-75 | 1 | 09731498 |  |  |
| 11 | CAB-E1-BNC | 1 |  |  |  |
| 12 | SF75BS-11.2.12P | 2 |  |  |  |
| 13 | PA-8T-V35 | 1 | 09724825 |  |  |
| 14 | CAB-OCT-V35-MT | 1 |  |  |  |
| 15 | POWER CORD | 2 |  |  |  |

| 二 、 | CATALYST 3200： |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 16 | WS-C3200B | 2 | 8010563, 7460482 | 正 常 |  |
| 17 | POWER CORD | 4 |  |  |  |
| 18 | CONSOLE CAB | 2 |  |  |  |
| 19 | WS-X3010 | 6 | 8080271, 8152055, 8152056, 8120262, 8120275, 8120282 |  |  |
| 20 | WS-X3002 | 2 | 8110291, 7360704 |  |  |
| 21 | 资 料 (套 ) | 2 |  |  |  |
| 三 、 | AS5300： |  |  |  |  |
| 22 | AS5300 | 1 | AAE98368203， 09365929 | 正 常 |  |
| 23 | POWER CORD | 1 |  |  |  |
| 24 | CONSOLE CABLE | 1 |  |  |  |
| 25 | AS53-E1-60DM | 1 | 09361210 |  |  |
| 26 | FR53-MMTL-60 | 1 |  |  |  |
| 27 | MEM- 16F-AS53 | 1 |  |  |  |
| 28 | CAB-E1-RJ45BNC | 2 |  |  |  |
| 29 | 资 料 (套 ) | 1 |  |  |  |
| 30 | PA-2CE1/PRI-75 | 1 | 09731319 |  |  |
| 31 | CAB-E1-BNC | 1 |  |  |  |
| 32 | 网 管 软 件 | CW-4.0-1VV | 1 |  |  |
| 33 | 资 料 (套) | 1 |  |  |  |

于  4月 5 日 开 始 安 装 玉 溪 中 心 网 络 设 备 ， 内 容 包 括中 心 交 换 机 Catalyst 3200 、 中 心 路 由 器 Cisco 7513、 语 音 路 由 器 As5300、 语 音 路 由 器 Cisco 3640 的 参 数 设 置 ， 并 进 行 相 应 的 连 通 性 和 功 能 测 试， 同 时 对 玉 溪 邮 政 局  技 术 人 员 进 行 现 场 培 训 ， 玉 溪 中 心  的 安 装 调 试 进 行 了  10天。

于  4月 16 日 开 始 安 装 大 理 中 心 网 络 设 备 ， 内 容 包括 中 心 交 换 机 Catalyst 3200 、 中 心 路 由 器 Cisco 7513、 语 音 路 由 器 As5300、 语 音 路 由 器 Cisco 3640 的 参 数 设 置 ， 并 进 行 相 应 的 连 通 性 和 功 能 测 试，并 对 大 理 邮 政 局 技 术 人 员 进 行 技 术培 训 ， 大 理 中 心 的 安 装 调 试 进 行 了 10天 。

地 州 的 安 装 调 试  从 4月 25日 到 10 月 份 基 本 结 束 ,  地 州 的 安 装 调 试 设 备 为 路 由 器 Cisco 2611、 AS 5300 语 音 设 备 、 Catalyst 2924 XL、 网 管 软 件 ， 调 通 的 内 容 为 地 州 中 心 局 域 网 分 别 与 大理 、 玉 溪 、 昆 明 中 心  的 连 通 ， 县 局、 地 州市 局 的 数 据 网 络 连 通以 及 IP 电 话 的 连 通 ， 同 时 对 各 地 州 进 行 现 场 培 训 。

以 下 为 各 地 州 的 安 装 调 试 情 况 ：

| 序号 | 名称 | 时 间 | 工 程 师 | 完 成 情 况 |
| --- | --- | --- | --- | --- |
| 1 | 昆 明 | 4/5-4/10 | 陈 力 | 完 成 |
| 2 | 大 理 | 4/15-5/25 | 黄 远 东 | 完 成 |
| 3 | 玉 溪 | 4/5-4/15 | 冯 根 怀 | 完 成 |
| 4 | 曲 靖 | 4/25-5/1 | 黄 远 东 | 完 成 |
| 5 | 红 河 | 5/4-5/11 | 陈 力 | 完 成 |
| 6 | 楚 雄 | 5/13-5/18 | 冯 根 怀 | 完 成 |
| 7 | 丽 江 | 5/25-6/1 | 黄 远 东 | 完 成 |
| 8 | 迪 庆 | 6/9-6/19 | 陈 力 | 完 成 |
| 9 | 临 沧 | 7/2-7/19 | 黄 远 东 | 完 成 |
| 10 | 保 山 | 7/13-7/29 | 陈 力 | 完 成 |
| 11 | 昭 通 | 8/5-8/29 | 黄 远 东 | 完 成 |
| 12 | 思 茅 | 8/23-9/2 | 陈 力 | 完 成 |
| 13 | 怒 江 | 8/6-8/15 | 冯 根 怀 | 完 成 |
| 14 | 版 纳 | 9/6-9/20 | 陈 力 | 完 成 |
| 15 | 德 宏 | 9/5-9/22 | 冯 根 怀 | 完 成 |

2、 验 收 报 告

## 于 10 月 3 日至 8 日  ， 在 云 南 省 邮政 局 绿 卡 工 程 昆 明 中 心  及 大 理 中 心 对 云 南省 邮 政 绿 卡 工 程 INTRANET 网 络 进 行 验 收 ， 参 加 验 收 人 员 ： 毛 芒 众 、 熊 晓 明 、 冯 根 怀 、 陈 力 、黄 远 东及 相 关 人 员 。

以下 为 测 试 内 容 ：

## (1)、 数 据 网 络 的 连 通 性 测 试

1）局 域 网 的 连 通 性 测 试

在 云 南 省 邮 政 局绿 卡 工 程 昆 明 中 心 的 任 一 台 计 算 机 上 ping 省 局 上 的 所 有 路 由 器 、 交 换 机 、 服 务 器 、 工 作 站 、 PC ， 均 能 ping 通 ， 说 明 省 局 昆 明 中 心 局 域 网 的 连 通 性。

在 大 理 分 中 心 的 任 一  台 计 算 机 上 ping 大 理 邮 政 局 绿 卡 工 程 网 络 上 的  所 有 路 由 器 、 交 换 机 、 服 务 器 、 工 作 站 、 PC ，均 能 ping 通 ， 说 明 大 理 中 心 邮 政 局 中 心 局 域 网 的 连 通 性 。

2） 广 域 网 的 连 通 性 测 试

在 省 邮 政 局 昆 明中 心 网 络 的 任 一 台 计 算 机 上 ping 省 邮 政 局 昆 明 中 心 以 外 的 其 他 中 心  、州 、 市 县 的 所 有 路 由 器 、 交 换 机 、 服 务 器 、 工作 站 、 PC ， 均 能 ping 通 ， 说 明 省邮 政 局 至 其 他 中 心 、 州 、市 县 的 广 域 网 的 连 通 性。

在 大 理 邮 政 局 中心 网 络 的 任一 台 计 算 机 上 ping 大 理 邮 政 局 以 外 的 其 他 中 心 、 州、市 县 及 省 局 昆 明 中 心 的 所 有 路 由 器 、 交 换机 、 服 务 器 、 工 作 站 、 PC ， 均 能 ping 通 ， 说 明 大 理 邮 政 局 中 心 至 其 它 地 方 的 广 域 网 的 连 通性 。

测 试 结 果 ：以 上 三  项 测 试 内 容 均 达 到 要 求 ， 且 速 度  较 快  。

## (2)、 IP 电 话 的 连 通 性 及 效 果 测 试

1)  从 省 邮 政 局 昆 明 中 心 到 其 他 中 心 的 IP 电 话 连 通性、 效 果 。

2)  从 省 邮 政 局 昆 明 中 心 到 其 他 州 、 县 市 的 IP 电 话连 通 性、 效 果 。

2)  从 大 理 邮 政 局 中 心 到 省 局 昆 明 中 心  的 IP  电 话 连 通 性、 效 果  。

3 ) 从 大 理 邮 政局 到 其 他 州 、 县 市 的 IP  电 话 连 通 性、 效 果。

## 测 试 结 果 ：以 上 测 试 内 容 均 已 连 通  ， 且 语 音 通 话 质 量 较 好 。

## (3)、 备 份 线 路 、 备 份 路 由 的 测 试

对 备 份 情 况 的 测 试，可 分 为 以 下 几 步 进 行：

1)  断 开 省 局 昆 明 中 心 到 测 试 地 州 DDN ， 测 试 是 否启 动 备 份 线 路、  备 份 路 由， 通 过show ip route、  show interfce、 telnet 、 ping 方 式 来 测 试， 以 及 IP 电 话 是 否 通 。

2) 恢 复 省 局 昆明 中 心 到 测 试 地 州   DDN ， 测 试 是 否从 备 份 线 路、  备 份 路 由 恢 复 到 DDN 及 主  路 由 工 作 状 态 ， 通 过 show ip route、  show interfce、  telnet 、 ping 方 式 来 测 试 。

## 测 试 结 果 ：以 上 测 试 内 容 均 已 到 到 要 求。

## (4)、 网 络 路 由 汇 聚 的 验 收 测 试

对 路 由 汇 聚 情 况 的  测 试，可 按 以 下  进 行：

检 查 网 络 设 备 配 置， 在 省 局 昆 明 中 心 中 心 路 由 器 及 其 他 中 心 的 路 由 器 上， 通 过 show configuration 命 令， 可 看 到 OSPF 的 路 由 配 置 上 的 路 由 汇 聚 命 令； 通 过 网 络 设 备 操 作 命 令 加 以 验证 各 AREA 之 内 的 网 络 路 由 信息 是 否 已 完  成 汇 聚。 在 各 中 心 的 中心 路 由 器 通 过 显 示 路 由 命 令， 确 认 各地 州、 县 市 的 路 由 信 息 是 通 过一 条 汇 总 信 息 到 达 各 中 心。

测试 结 果 ：以 上 测 试 内 容 均 已 到 到 要 求 。

## (5)、 网 管 系 统 的 功 能 测 试

1） 验 证 网 管 软件 的 安 装 正 常

观 察 网 管 软 件 的 安 装 文 件（.Log 文 件），核 实 是 否 有 错 误 提 示 信 息。

2）验 证 网 管 软 件 的功 能 正 常

网 管 软 件 完 成 后，可 保 证 以 下 功 能：

网 络 拓 扑 图 的 生 成；

网 络 设 备 的 图 形 显 示 （即 CISCO  view）;

网 络 设 备 的 WEB 界 面 管 理 功 能；

交 换 机 流 量 分 析（Traffice Director）

Vlan  拓 扑

测试 结 果 ：以 上 测 试 内 容 均 已 到 到 要 求 。

3、 IP 地 址 分 配 表

| 昆 明 | 151.240.1.X-151.240.20.X |
| --- | --- |
| 大 理 | 151.240.21.X-151.240.40.X |
| 玉 溪 | 151.240.41.X-151.240.57.X |
| 曲 靖 | 151.240.58.X-151.240.74.X |
| 红 河 | 151.240.75.X-151.240.91.X |
| 楚 雄 | 151.240.92.X-151.240.108.X |
| 丽 江 | 151.240.109.X-151.240.125.X |
| 迪 庆 | 151.240.126.X-151.240.135.X |
| 临 沧 | 151.240.136.X-151.240.145.X |
| 保 山 | 151.240.146.X-151.240.159.X |
| 昭 通 | 151.240.160.X-151.240.170.X |
| 施 茅 | 151.240.171.X-151.240.185.X |
| 怒 江 | 151.240.186.X-151.240.195.X |
| 版 纳 | 151.240.196.X-151.240.205.X |
| 德 宏 | 151.240.206.X-151.240.215.X |

|  | 局名 | WAN主链路 | WAN 第二链路 |
| --- | --- | --- | --- |
| 至 | 昆 明 | 151.240.20．5/30 | 151.240．20．105/30 |
|  | 大 理 | 151.240．20．9/30 | 151.240．20．109/30 |
|  | 玉 溪 | 151.240．20．13/30 | 151.240．20．113/30 |
|  | 曲 靖 | 151.240．20．17/30 | 151.240．20．117/30 |
|  | 红 河 | 151.240．20．21/30 | 151.240．20．121/30 |
|  | 楚 雄 | 151.240．20．25/30 | 151.240．20．125/30 |
|  | 丽 江 | 151.240．20．29/30 | 151.240．20．129/30 |
|  | 迪 庆 | 151.240．20．33/30 | 151.240．20．133/30 |
|  | 临 沧 | 151.240．20．37/30 | 151.240．20．137/30 |
|  | 保 山 | 151.240．20．41/30 | 151.240．20．141/30 |
|  | 昭 通 | 151.240．20．45/30 | 151.240．20．145/30 |
|  | 施 茅 | 151.240．20．49/30 | 151.240．20．149/30 |
|  | 怒 江 | 151.240．20．53/30 | 151.240．20．153/30 |
|  | 版 纳 | 151.240．20．57/30 | 151.240．20．157/30 |
|  | 德 宏 | 151.240．20．61/30 | 151.240．20．161/30 |

4、 IP 电 话 号 码 表

云 南 省 邮 政 绿 卡 工 程 INTRANET 网 络 IP 电 话 号 码 分  配如 下 ：

|  | 号 码 |
| --- | --- |
| 昆 明 | 1001 |
| 大 理 | 1002 |
| 玉 溪 | 1003 |
| 曲 靖 | 1004 |
| 红 河 | 1005 |
| 楚 雄 | 1006 |
| 丽 江 | 1007 |
| 迪 庆 | 1008 |
| 临 沧 | 1009 |
| 保 山 | 1010 |
| 昭 通 | 1011 |
| 思 茅 | 1012 |
| 怒 江 | 1013 |
| 版 纳 | 1014 |
| 德 宏 | 1015 |

5、 设 备 技 术 参 数

| 设备 | 重量kg | 工作温度℃ | 体积cm | 耗电量w |
| --- | --- | --- | --- | --- |
| Cisco 7513 | 72.58 | (-4 至 45) | 85.73*44.45*55.88 | 1200/1700 |
| Catalyst 3200 | 39 | (0 至 40) | 43*34*14 | 100 |
| Cisco 3640 | 13.6 | (0 至 40) | 8.7*44.5*40.0 | 140w |
| As5300 | 14.5 | (0 至 40) | 8.6*44.45*46.3 | 400W |
| Cisco 2611 | 4.66 | (0 至 40) | 4.3*44.45*30.00 | 72 |
| Catalyst 2924 | 18 | (-4 至 45) | 4.5*44.5*36.2 | 80 |

6. 设 备 配 置 参 数(以玉 溪 为 例 )

1、 玉 溪 中 心 路 由 器 CISCO 7513 配 置

!

version 11.3

no service password-encryption

!

hostname yx7513

!

enable secret 5 $1$eTmD$BMqQviqYQRLbqIFLrH9GV1

enable password cisco

!

ip subnet-zero

!

controller E1 5/0/0

channel-group 0 timeslots 1

channel-group 1 timeslots 2

channel-group 2 timeslots 3

channel-group 3 timeslots 4

channel-group 4 timeslots 5

channel-group 5 timeslots 6

channel-group 6 timeslots 7

channel-group 7 timeslots 8

channel-group 8 timeslots 9

channel-group 9 timeslots 10

channel-group 10 timeslots 11

channel-group 11 timeslots 12

channel-group 12 timeslots 13

channel-group 13 timeslots 14

channel-group 14 timeslots 15

channel-group 15 timeslots 17

channel-group 16 timeslots 18

channel-group 17 timeslots 19

channel-group 18 timeslots 20

channel-group 19 timeslots 21

channel-group 20 timeslots 22

channel-group 21 timeslots 23

channel-group 22 timeslots 24

channel-group 23 timeslots 25

channel-group 24 timeslots 26

channel-group 25 timeslots 27

channel-group 26 timeslots 28

channel-group 27 timeslots 29

channel-group 28 timeslots 30

channel-group 29 timeslots 31

!

controller E1 5/0/1

channel-group 0 timeslots 1

channel-group 1 timeslots 2

channel-group 2 timeslots 3

channel-group 3 timeslots 4

channel-group 4 timeslots 5

channel-group 5 timeslots 6

channel-group 6 timeslots 7

channel-group 7 timeslots 8

channel-group 8 timeslots 9

channel-group 9 timeslots 10

channel-group 10 timeslots 11

channel-group 11 timeslots 12

channel-group 12 timeslots 13

channel-group 13 timeslots 14

channel-group 14 timeslots 15

channel-group 15 timeslots 17

channel-group 16 timeslots 18

channel-group 17 timeslots 19

channel-group 18 timeslots 20

channel-group 19 timeslots 21

channel-group 20 timeslots 22

channel-group 21 timeslots 23

channel-group 22 timeslots 24

channel-group 23 timeslots 25

channel-group 24 timeslots 26

channel-group 25 timeslots 27

channel-group 26 timeslots 28

channel-group 27 timeslots 29

channel-group 28 timeslots 30

channel-group 29 timeslots 31

!

interface FastEthernet4/0/0

no ip address

no ip mroute-cache

bridge-group 1

!

interface FastEthernet4/1/0

no ip address

no ip mroute-cache

bridge-group 1

!

interface Serial5/0/0:29

no ip address

no ip mroute-cache

!

interface Serial5/0/0:28

no ip address

no ip mroute-cache

!

interface Serial5/0/0:27

no ip address

no ip mroute-cache

!

interface Serial5/0/0:26

no ip address

no ip mroute-cache

!

interface Serial5/0/0:25

no ip address

no ip mroute-cache

!

interface Serial5/0/0:24

no ip address

no ip mroute-cache

!

interface Serial5/0/0:23

no ip address

no ip mroute-cache

!

interface Serial5/0/0:22

no ip address

no ip mroute-cache

!

interface Serial5/0/0:21

description DDN to JIANSHUI_JIANZHONGLU

ip address 151.240.4.105 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:20

description DDN TO LULIANG

ip address 151.240.4.81 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:19

description DDN TO XIANWEI

ip address 151.240.4.77 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:18

description DDN to LUOPING

ip address 151.240.4.73 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:17

description DDN to ZHANYU

ip address 151.240.4.69 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:16

description DDN TO MALONG

ip address 151.240.4.65 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:15

description DDN TO SHIZONG

ip address 151.240.4.61 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:14

description DDN TO XUNDIAN

ip address 151.15.4.57 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:13

description DDN to FUYUAN

ip address 151.240.4.53 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:12

description DDN TO HUIZE-2

ip address 151.15.4.49 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:11

description DDN TO HUIZE-1

ip address 151.240.4.45 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:10

description DDN TO YANJIANG

ip address 151.240.4.41 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:9

description DDN TO XINGPING

ip address 151.15.4.37 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:8

description DDN TO E'SHAN-2

ip address 151.15.4.33 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:7

description DDN TO E'SHAN-1

ip address 151.240.4.29 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:6

description DDN TO YIMENG

ip address 151.240.4.25 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:5

description DDN TO CHENGJIANG

ip address 151.240.4.21 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:4

description DDN TO JIANGCHUAN-JIANGCHENG

ip address 151.15.4.17 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:3

description DDN TO JINGCHUAN-XINGYUNLU

ip address 151.240.4.13 255.255.255.252

no ip mroute-cache

no cdp enable

!

interface Serial5/0/0:2

description DDN TO HUALING

ip address 151.240.4.9 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:1

description DDN TO TONGHAI-XINGDALOU

ip address 151.240.4.5 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/0:0

description DDN TO TONGHAI-NANJIE

ip address 151.15.4.1 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:29

no ip address

no ip mroute-cache

!

interface Serial5/0/1:28

no ip address

no ip mroute-cache

!

interface Serial5/0/1:27

no ip address

no ip mroute-cache

!

interface Serial5/0/1:26

no ip address

no ip mroute-cache

!

interface Serial5/0/1:25

no ip address

no ip mroute-cache

!

interface Serial5/0/1:24

description DDN TO YANSHAN-PINGYUANJIE

ip address 151.15.4.185 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:23

description DDN TO YANSHAN-1

ip address 151.240.4.181 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:22

description DDN TO MALIPO

ip address 151.240.4.177 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:21

description DDN TO QIUBEI

ip address 151.240.4.173 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:20

description DDN TO XUCHOU

ip address 151.240.4.169 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:19

description DDN TO GUANGNAN

ip address 151.240.4.165 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:18

description DDN TO FUNING-2

ip address 151.15.4.161 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:17

description DDN TO FUNING-1

ip address 151.240.4.157 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:16

description DDN TO MAGUANG

ip address 151.240.4.153 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:15

description DDN TO HEKUO

ip address 151.15.4.149 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:14

description DDN TO LUCHUEN

ip address 151.15.4.145 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:13

description DDN TO JINGPING

ip address 151.15.4.141 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:12

description DDN TO HONGHE

ip address 151.15.4.137 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:11

description DDN TO YANYANG

ip address 151.15.4.133 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:10

description DDN TO LUXI

ip address 151.240.4.129 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:9

description DDN TO MILE-XINGYINGYETING

ip address 151.15.4.125 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:8

description DDN TO MILE-1

ip address 151.240.4.121 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:7

description DDN TO SHIPING

ip address 151.15.4.113 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:6

description DDN TO JIANSHUI-YINHUIBEILU

ip address 151.15.4.109 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:5

no ip address

no ip mroute-cache

!

interface Serial5/0/1:4

description DDN TO PINGBIAN

ip address 151.15.4.101 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:3

description DDN TO MENZI-RENMINGZHONGLU

ip address 151.15.4.97 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:2

description DDN TO MENZI-1

ip address 151.240.4.93 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:1

description DDN TO KAIYUAN-2

ip address 151.15.4.89 255.255.255.252

no ip mroute-cache

!

interface Serial5/0/1:0

description DDN TO KAIYUAN-1

ip address 151.15.4.85 255.255.255.252

no ip mroute-cache

!

interface Serial5/1/0

no ip address

encapsulation x25

no ip mroute-cache

shutdown

!

interface Serial5/1/1

no ip address

shutdown

!

interface Serial5/1/2

no ip address

shutdown

!

interface Serial5/1/3

description

no ip address

!

interface Serial5/1/4

no ip address

shutdown

!

interface Serial5/1/5

no ip address

shutdown

!

interface Serial5/1/6

no ip address

shutdown

!

interface Serial5/1/7

no ip address

shutdown

!

interface Async1

no ip address

shutdown

!

interface BVI1

ip address 151.240.0.12 255.255.255.0

!

router eigrp 877

network 151.15.0.0

network 151.240.0.0

!

no ip classless

ip route 151.240.11.160 255.255.255.224 151.240.254.4 230

ip route 151.240.11.224 255.255.255.224 151.240.254.3 230

snmp-server community public RW

snmp-server host 151.240.0.5 public

bridge irb

bridge 1 protocol ieee

bridge 1 route ip

!

line con 0

password cisco

login

line aux 0

line vty 0 4

password yhpass

login

!

end

2、 中 心 语 音 路 由 器AS5300 配 置

hostname guangnan

!

enable secret 5 $1$9uRX$6h6j4CEXyKlP3WnjzJwuJ/

!

username yxlk5300 password 0 cisco

chat-script lk ABORT ERROR ABORT BUSY "" "ATDT \T" TIMEOUT 60 CONNECT \c  username:guangnan password:cisco

!

dial-peer voice 1 voip

destination-pattern 77000

session target ipv4:151.240.0.14

req-qos guaranteedDelay

!

dial-peer voice 2 voip

destination-pattern 77001

session target ipv4:151.240.0.14

req-qos guaranteedDelay

!

dial-peer voice 79 voip

destination-pattern 76011

session target ipv4:151.240.4.174

req-qos guaranteedDelay

!

dial-peer voice 80 voip

destination-pattern 76012

session target ipv4:151.240.4.174

req-qos guaranteedDelay

!

dial-peer voice 81 voip

destination-pattern 76021

session target ipv4:151.240.4.170

!

dial-peer voice 82 voip

destination-pattern 76022

session target ipv4:151.240.4.170

req-qos guaranteedDelay

!

dial-peer voice 83 voip

destination-pattern 76031

session target ipv4:151.240.4.154

req-qos guaranteedDelay

!

dial-peer voice 84 voip

destination-pattern 76032

session target ipv4:151.240.4.154

req-qos guaranteedDelay

!

dial-peer voice 85 voip

destination-pattern 76041

session target ipv4:151.240.4.178

req-qos guaranteedDelay

!

dial-peer voice 86 voip

destination-pattern 76042

session target ipv4:151.240.4.178

req-qos guaranteedDelay

!

dial-peer voice 87 voip

destination-pattern 76051

session target ipv4:151.240.4.158

req-qos guaranteedDelay

!

dial-peer voice 88 voip

destination-pattern 76052

session target ipv4:151.240.4.158

req-qos guaranteedDelay

!

dial-peer voice 89 pots

destination-pattern 76061

port 1/0/0

!

dial-peer voice 90 pots

destination-pattern 76062

port 1/0/1

!

dial-peer voice 91 voip

destination-pattern 76071

session target ipv4:151.240.4.182

!

dial-peer voice 92 voip

destination-pattern 76072

session target ipv4:151.240.4.182

!

dial-peer voice 93 voip

destination-pattern 76073

session target ipv4:151.240.4.186

!

dial-peer voice 94 voip

destination-pattern 76074

session target ipv4:151.240.4.186

!

!

voice-port 1/0/0

!

voice-port 1/0/1

!

!

!

interface Ethernet0/0

ip address 151.240.11.97 255.255.255.224

!

interface Serial0/0

backup delay 2 2

backup interface Async65

ip address 151.240.4.166 255.255.255.252

ip rtp header-compression

ip rtp compression-connections 25

ip rsvp bandwidth 16 16

fair-queue 64 256 36

!

interface Ethernet0/1

no ip address

shutdown

!

interface Serial0/1

no ip address

shutdown

!

interface Async65

ip unnumbered Ethernet0/0

encapsulation ppp

shutdown

dialer in-band

dialer map ip 151.240.0.13 name yxlk5300 modem-script lk broadcast 169

dialer-group 1

async dynamic address

async dynamic routing

async mode dedicated

no peer default ip address

no cdp enable

ppp authentication chap

!

router eigrp 877

network 151.240.0.0

!

ip classless

ip route 0.0.0.0 0.0.0.0 Serial0/0 10

ip route 0.0.0.0 0.0.0.0 Async65 100

dialer-list 1 protocol ip permit

snmp-server community public RW

snmp-server host 151.240.0.5 traps public

!

line con 0

exec-timeout 0 0

line aux 0

modem InOut

modem autoconfigure discovery

transport input all

stopbits 1

speed 115200

flowcontrol hardware

line vty 0 4

password mtt1999

login

!

end

3、 分 支 路 由 器CISCO 2611 配 置

!

version 11.3

service timestamps debug uptime

service timestamps log uptime

no service password-encryption

!

hostname guangnan

!

enable secret 5 $1$9uRX$6h6j4CEXyKlP3WnjzJwuJ/

!

username yxlk5300 password 0 cisco

chat-script lk ABORT ERROR ABORT BUSY "" "ATDT \T" TIMEOUT 60 CONNECT \c  username:guangnan password:cisco

!

dial-peer voice 1 voip

destination-pattern 77000

session target ipv4:151.240.0.14

req-qos guaranteedDelay

!

dial-peer voice 2 voip

destination-pattern 77001

session target ipv4:151.240.0.14

req-qos guaranteedDelay

!

dial-peer voice 79 voip

destination-pattern 76011

session target ipv4:151.240.4.174

req-qos guaranteedDelay

!

dial-peer voice 80 voip

destination-pattern 76012

session target ipv4:151.240.4.174

req-qos guaranteedDelay

!

dial-peer voice 81 voip

destination-pattern 76021

session target ipv4:151.240.4.170

!

dial-peer voice 82 voip

destination-pattern 76022

session target ipv4:151.240.4.170

req-qos guaranteedDelay

!

dial-peer voice 83 voip

destination-pattern 76031

session target ipv4:151.240.4.154

req-qos guaranteedDelay

!

dial-peer voice 84 voip

destination-pattern 76032

session target ipv4:151.240.4.154

req-qos guaranteedDelay

!

dial-peer voice 85 voip

destination-pattern 76041

session target ipv4:151.240.4.178

req-qos guaranteedDelay

!

dial-peer voice 86 voip

destination-pattern 76042

session target ipv4:151.240.4.178

req-qos guaranteedDelay

!

dial-peer voice 87 voip

destination-pattern 76051

session target ipv4:151.240.4.158

req-qos guaranteedDelay

!

dial-peer voice 88 voip

destination-pattern 76052

session target ipv4:151.240.4.158

req-qos guaranteedDelay

!

dial-peer voice 89 pots

destination-pattern 76061

port 1/0/0

!

dial-peer voice 90 pots

destination-pattern 76062

port 1/0/1

!

dial-peer voice 91 voip

destination-pattern 76071

session target ipv4:151.240.4.182

!

dial-peer voice 92 voip

destination-pattern 76072

session target ipv4:151.240.4.182

!

dial-peer voice 93 voip

destination-pattern 76073

session target ipv4:151.240.4.186

!

dial-peer voice 94 voip

destination-pattern 76074

session target ipv4:151.240.4.186

!

!

voice-port 1/0/0

!

voice-port 1/0/1

!

!

!

interface Ethernet0/0

ip address 151.240.11.97 255.255.255.224

!

interface Serial0/0

backup delay 2 2

backup interface Async65

ip address 151.240.4.166 255.255.255.252

ip rtp header-compression

ip rtp compression-connections 25

ip rsvp bandwidth 16 16

fair-queue 64 256 36

!

interface Ethernet0/1

no ip address

shutdown

!

interface Serial0/1

no ip address

shutdown

!

interface Async65

ip unnumbered Ethernet0/0

encapsulation ppp

shutdown

dialer in-band

dialer map ip 151.240.0.13 name yxlk5300 modem-script lk broadcast 169

dialer-group 1

async dynamic address

async dynamic routing

async mode dedicated

no peer default ip address

no cdp enable

ppp authentication chap

!

router eigrp 877

network 151.240.0.0

!

ip classless

ip route 0.0.0.0 0.0.0.0 Serial0/0 10

ip route 0.0.0.0 0.0.0.0 Async65 100

dialer-list 1 protocol ip permit

snmp-server community public RW

snmp-server host 151.240.0.5 traps public

!

line con 0

exec-timeout 0 0

line aux 0

modem InOut

modem autoconfigure discovery

transport input all

stopbits 1

speed 115200

flowcontrol hardware

line vty 0 4

password mtt1999

login

!

end